## Slide 1: JATTU TRUST Progress report 30.06.16

## Slide 2: Details of the projects in the State of Andhra Pradesh
Name of the PIA | Year of inception | Name of the districts | Name of the blocks | Number of villages | No. of Mahila Kisan |  | Area covered
 |  |  |  |  | Targeted | Covered | 
Jattu Trust | 2013 | Vizianagaram | G.L.Puram |  | 1500 | 1457 | 728.5 Acres
 |  |  | Kurupam |  | 1000 | 841 | 420.5 Acres
 |  |  | Garugubilli |  | 200 | 132 | 66 Acres
 |  |  | Komarada |  | 100 | 27 | 13.5Acres
 |  |  | J.M. Valasa |  | 100 | - | 
 |  |  | Parvathipuram |  | 100 | - | 
 |  | Total |  | 150 | 3000 | 2457 | 1228.5 Acres

## Slide 3: MKSP areas in the State of Andhrapradesh (please insert a map)
Vizianagaram |  | 

## Slide 4: Community institution architecture for MKSP (consolidated)
 | Generic women institutions | Livelihoods based institutions | Interface/ Coordination mechanism | Activities undertaken by LH institutions
Village Level | Self Help Groups 320 SHGs covered | 150 Annapurna pantala Sangams 105 covered | CRP locally monitoring and organize weekly meetings at village level | Promotes Annapurna crop models. Build capacities on pre and post harvesting techniques and Collects village level produces
GP level |  |  |  | 
Cluster Level | Village Organization 47 Vos covered | 8 Cluster Federations | Para professional organize cluster level meetings at cluster head quarters | Promotes value addition activities, processing and marketing. Conduct trainings, Mapping resources, planning procurement
Block level | Mandala Mahila Samakhya 4 covered |  |  | 
District Level | Zilla Samakhya | 1 MACS | Project manager/Senior professional co-ordinate Clusters/ MACS . | Promotes value addition activities, processing and marketing. Conduct trainings, Mapping resources, planning procurement , handling greviences and documentation of best practices and co-ordinate all 8 cluster federations.
State Level |  |  |  | 

## Slide 5: Main interventions under sustainable agriculture practices in your state * ½ Acre Annapurna model of cultivation, Bedding, Trenching, Furrowing and Plantation * Practicing Non pesticide management methods and promoting their traditional methods

## Slide 6: Physical progress- SA/NTFP (consolidated)
Particulars | Target as per sanction order/DPR | Cumulative achievement till last reporting quarter | Achievement in the current quarter | Plan for the next quarter
No. of Mahila Kisan covered-SA/NTFP activities | 3000 | 2431 | 26 | 250
No. of Mahila Kisan in NRLM compliant SHGs | 3000 | 2431 | 26 | 
No. of trainee days completed on SA/NTFP for Mahila Kisan | 9000 | 5934 | - | 1359
No. of Producer groups formed | 150 | 80Village level,7Cluster level | 25 | 25
No. of Mahila Kisan in the fold of PGs | 3000 | 1923 | 200 | 308
Total No. of HHs adopting SA/NTFP practices | 3000 | 2431 | 26 | 250
No. of training modules developed-SA/NTFP |  |  |  | 
Print | 4 | 3 |  | 
AV | 4 | 2 |  | 1
No. of training modules used for training-SA/NTFP |  |  |  | 
Print | 4 | 3 |  | 
AV | 4 | 2 |  | 

## Slide 7: Physical progress-CRP creation-SA/NTFP/Livestock activities (consolidated)
Particulars | Target as per sanction order/DPR | Cumulative achievement till last reporting quarter | Achievement in the current quarter | Plan for the next quarter
No. of CRPs identified | 500 | 150 | 80 | 100
No. of CRPs trained and deployed | 30 | 30 |  | 
No. of training modules developed for CRP training |  |  |  | 
Print | 4 | 3 |  | 
AV | 4 | 2 |  | 
No. of trainee days of training for CRPs | 180 | 180 |  | 

## Slide 8: MKSP Progress (consolidated)
 | Target as per sanction order/DPR | Cumulative achievement till last reporting quarter | Achievement in the current quarter | Plan for the next quarter
Net cropped area (Acres/ Models) under SA for Kharif season crops | 2431 models/1212.5Acres | 1215.5 | - | 250
Net cropped area (Acres) under SA practices for Rabi crops | 2701 models/1350.5 acres |  |  | 

## Slide 9: Physical progress-Livestock activities
Total No. of Mahila Kisan covered till date: 2457
Total no. of HHs covered till date: 2457
Total No. of Producer Groups formed: 105
Total No. of Para professionals trained and deployed at village level: 8

## Slide 10: Output measurement… (give consolidated figures)
Parameters | Status as per baseline | Current status | % increase over baseline
Total volume of Major crop-output/NTFP (Major product) produced (quintals) | Practicing only mono cropping in 40% of fields remaining were barren lands. | Practicing mixed crops | 100%
Gross output of agri-intervention (Major Crop) only/NTFP activity (in Rs. Lakhs) | Rs.4862000/- | Rs.26538212/- | 400%
No. of crops /NTFP produce marketed through collective marketing |  | 2 | Vegitables, lemon grass marketed through collective marketing. Remarks : ½ Acre Annapurna crop model objective is improve food security among families
No. of Mahila Kisan benefited through collective marketing |  | 160 | 

## Slide 11: Training Module Development
.
Name of the Theme on which module developed | Type of training module | Number/units developed so far
TOT for CRP (grooming) | Annapurna model of agriculture practices | 1
Agriculture | Traditional agricultural practices in Parvathipuram Tribal area | 1
Gender |  | 
Community Institution building | Organization of pantala sanghams. Rolls and responsibilities of office bearers / CRPs / C.Cs / Project Manager | Included in Annapurna model of Agriculture practices booklet
Training of project management/ execution team | -do- | -do-
Natural Resource Management | Preparation of Natural decortions | -do-

## Slide 12
Name of training module | No. of beneficiaries trained | mode of training/CB | Total training days | Resource agencies/ Persons who have imparted training
Understanding on Traditional Agriculture and modern agriculture | 1978 | Class room training, field visit, and learning by doing | 5934 | Jattu Trust, C.C, T.C and P.M
Natural Agricultural scientists and other Govt Institutions. Working on organic Agriculture | “ | “ | “ | Jattu Trust, C.C, T.C and P.M
Non negotiables in organic agriculture practices. | “ | “ | “ | Jattu Trust, C.C, T.C and P.M
Annapurna model of agriculture practices | “ | “ | “ | Jattu Trust, C.C, T.C and P.M
Total no. of Modules: 4 | Total 1978 |  | Total no. of days 5934 | 

## Slide 13
Name of training module | No. of CRPs/PRPs trained | mode of training/CB | Total training days | Resource agencies/ Persons who have imparted training
Understanding on traditional Agriculture and modern agriculture | 30 | Class room training, field visit, and learning by doing | 180 | Jattu Trust Executive Trustee, PM MKSP and T.C
Natural Agricultural scientists and other Govt. institutions working on organic Agriculture | “ | “ | “ | “
Non negotiables in organic Agriculture practices | “ | “ | “ | “
Beneficiaries and Harmful insects | “ | “ | “ | “
Annapurna model of agriculture practices | “ | “ | “ | “
Total no. of Modules: 5 | Total: 30 |  | Total no. of days :180 | 

## Slide 14
Name of training module | No. of Project staffs trained (CCs, TCs , Project Manager) | mode of training/CB | Total training days | Resource agencies/ Persons who have imparted training
Traditional and Modern Agriculture | 8 | Class room training, field visit, and learning by doing | 48 | Jattu Trust
Natural Agriculture Scientists and other Departments, Institutions working on organic farming | “ | “ | “ | “
Non negotiables in organic Agriculture | “ | “ | “ | “
Beneficiary and Harmful insects in organic agriculture | “ | “ | “ | “
Annapurna model of Agriculture practices | “ | “ | “ | “
Institution building | “ | “ | “ | “
Annapurna pantala sangham at village level, cluster level and project level | “ | “ | “ | “
Total no. of Modules | Total 8 |  | Total no. of days 48 | 

## Slide 15: Physical asset creation
Source of Funds | Name of the Asset/ Infrastructure created/ given | Number | Total Value of assets
MKSP and 20% community labour contribution | Trench around the Bunds 1.5 x1 width x depth ,Furrows with seven feet gap ,Fruit plants, Fencing around the bunds | 2431 | 17017000
MKSP | Water tubs | 608 | 126909
Source of Funds | Name of the Asset/ Infrastructure created/ given | Number | Total Value of assets
Convergence with agriculture Dept | Oil engines, water carrying pipes and power weedors. | 5 oil engines, 175 pipes, 1Weedor, 1 Grass cutter | 170240
Convergence with Nabard | Solar pump set | 1 | 184348
Total |  |  | 481497
Individual level
Community Level

## Slide 16: Public disclosures

## Slide 17: Thanks…